## Slide 1
3-years Investment Program of the IOFS Secretariat, planned for implementation out the regular budget, for 2020-2022
№ | PROGRAMME AND ACTIVITIES | ADOPTED BUDGET 2020 | DRAFT BUDGET 2021 | DRAFT BUDGET 2022
1 | Feasibility studies/Documentation | 500 000 | 1 000 000 | 1 000 000
1.1 | Establishment of IOFS Grain Fund | 500 000 | - | 
1.2 | Agriculture Investment Fund of IOFS | - | 500 000 | -
1.3 | IOFS transport and logistics center | - | 500 000 | -
1.4 | IOFS center of scientific and technological development | - |  | 500 000
4 | IOFS online commodity exchange | - | - | 500 000
5 | Food security database platform of IOFS | 500 000 | - | -
6 | TOTAL | 1 000 000 | 1 000 000 | 1 000 000
In U.S. dollars

## Slide 2
Schedule for the realization of activities in 2020
№ | Stages of realization | Jan.-Feb | March | Apr.-Sep | Okt.-Nov | Dec. | 2021
1 | Preparation of technical specifications and its approval with interested parties |  |  |  |  |  | 
2 | Competitive selection of a consultant to develop a feasibility study |  |  |  |  |  | 
3 | Realization period |  |  |  |  |  | 
4 | Providing the final report and its approval with stakeholders |  |  |  |  |  | 
5 | Establishment and operation of the Grain Fund |  |  |  |  |  | 
Grain Fund
№ | Stages of realization | Jan.-Feb | Mar.- Apr. | May-Sep. | Oct.-Dec. | 2021
1 | Refinement of the country’s food security database, taking into account comments and suggestions from stakeholders |  |  |  |  | 
2 | Promotion of a portal with a database among enterprises of OIC countries, members of the Islamic Association of Agricultural Producers |  |  |  |  | 
3 | Collection, filling of the database with necessary data and their updating. |  |  |  |  | 
4 | Creation of a section on business initiatives on the portal database (investment projects, trading offers, transportation, implementation of new technologies, etc.) |  |  |  |  | 
5 | Launch on the trading platform database portal of food products among OIC countries |  |  |  |  | 
Database